## SRS Progress
Revision | Description of Changes | Responsible Team Member(s) | Version | Date | Link to the Document
Ninth Revision | Added a structured System Testing section in- cluding test case conventions, standardized leg- ends (F, N, B, P, R), and formal test documen- tation format. Also incorporated API and route testing using the Bruno client within the testing approach. | Yash Bavadiya, Chaitanya Singh | 2.2 | 2026-03-18 | SRS 2.2
Eighth Revision | Minor revision: added a clearer Non-Functional Requirements (NFR) section with better-defined system qualities, along with small wording improvements and formatting refinements. No major structural or feature changes. | Yash Bavadiya | 2.1 | 2026-02-15 | SRS 2.1
Seventh Revision | Major consolidated revision: removed ambulance module, finalized PostgreSQL-based architecture, updated class/sequence/activity diagrams, expanded functional and non-functional requirements, improved security and compliance sections, and prepared complete SRS for formal submission. | Yash Bavadiya, Chaitanya Singh, Nayan Patidar | 2 | 2026-02-04 | SRS 2.0
Sixth Revision | Added development methodology, sprint planning strategy, coding conventions, project management structure, and team ownership responsibilities to support implementation readiness. | Yash Bavadiya, Chaitanya Singh, Nayan Patidar | 1.6 | 2026-02-02
Fifth revision | Added External Medical Document Digitization feature; expanded laboratory and pharmacy workflows; improved traceability between modules and database entities. | Nayan Patidar | 1.5 | 2026-02-01
Fourth Revision | Added Doctor scheduling, availability management, attendance tracking, and overtime calculation requirements; updated related activity diagrams. | Chaitanya Singh | 1.4 | 2026-01-30
Third Revision | Introduced QR-based patient identification and automated check-in workflow; added VisitID concept for linking consultations, prescriptions, laboratory reports, and billing records. | Nayan Patidar | 1.3 | 2026-01-27
Second Revision | Expanded authentication design to include institutional LDAP-based login and strengthened security constraints for handling medical data. | Chaitanya Singh | 1.2 | 2026-01-24
First Revision | Refined requirement statements for clarity; standardized REQ-XX identifiers; improved formatting and IEEE structure; reorganized sections for consistency. | Yash Bavadiya | 1.1 | 2026-01-22
Initial Version | Initial SRS draft defining core PHC system features including authentication, patient records, prescriptions, laboratory, pharmacy, billing, and ambulance booking modules. Baseline functional and non-functional requirements documented. | Yash Bavadiya, Chaitanya Singh, Nayan Patidar | 1 | 2026-01-21 | SRS 1.0

## UML Progress
Date | Diagram Category | Updates | Version_No. | Approved by | Link to that
Use-Case Diagram
2026-01-21 | Usecase (Initial Conceptual Model) | - Created initial high-level use case model for the PHC Integrated Digital System. - Identified 7 primary actors: Patient, Doctor, Admin, Pharmacy, Nurse, LabStaff, and AmbulanceStaff. - Mapped basic, direct actor-to-use-case associations. - Included a centralized "Login" use case shared across multiple staff roles. - Captured core isolated functionalities like booking appointments, viewing lab reports, and managing inventory. | 0 | Nayan Patidar, Yash Bavadiya, Chaitanya Singh | https://drive.google.com/file/d/1loGLwa-gQuiD6xrQrDm1OQ1gdDsMY7nf/view?usp=sharing
2026-02-04 | Usecase (Refined UML) | - Refined actor roles to align with system workflow: Added Reception Staff, renamed "Pharmacy" to Pharmacy Staff. - Introduced advanced relationships (dashed lines) to represent internal dependencies and sequential workflows (e.g., Create Visit -> Add to Doctor Queue). - Integrated an external system actor (LDAP System) to model authentication. - Replaced the centralized "Login" with specific functional entry points. - Expanded scope with new specific use cases (e.g., Enter Vitals, Set Availability). | 1 | Nayan Patidar, Yash Bavadiya | https://drive.google.com/file/d/1-qsm99t2vkocEdGyY3rJouB4zd1i5vwm/view?usp=sharing
2026-02-14 | Usecase (Refined UML) | - Reviewed and validated the V2.0 use-case model against finalized functional requirements. - Verified actor-to-use-case mappings for strict consistency with the textual use-case descriptions in the SRS. - Conducted minor formatting and layout adjustments to improve document readability. - Confirmed no major structural changes or new actors were required for this system iteration. | 2 | Nayan Patidar, Chaitanya Singh | *same as above*
Activity Diagram
2026-01-21 | Activity (Initial Booking Flow) | - Created initial end-to-end activity diagram modeling the complete patient journey. - Modeled a single, continuous, top-to-bottom flow combining multiple actor steps (Patient, Doctor, Lab, Pharmacy) without swimlanes or role isolation. - Captured basic sequential logic from appointment booking to prescription, lab tests, and billing. - Included basic decision diamonds for conditional paths (Lab Test Required?, Medicine Required?, Emergency?). | 0 | Chaitanya, Nayan | https://drive.google.com/file/d/1270c2A-Si69AnG1dMSr5IhLqfavAMsUt/view?usp=sharing
2026-02-04 | Activity - Patient | - Decomposed the monolithic V1.0 flow to isolate Patient-specific interactions. - Introduced a central "Patient Dashboard" to act as a state hub. - Replaced the linear sequential flow with an event-driven structure, modeling parallel functional paths (Medical Records, Prescriptions, QR Appointments, Billing) branching from a main "Select Function" decision node. | 1 | Chaitanya | https://drive.google.com/file/d/19Ovv2M3huZmrernyMg6lMM3idtHyTM7e/view?usp=sharing
2026-02-04 | Activity - Reception | - Created a dedicated activity flow for the newly formalized Reception Staff workflow. - Modeled the physical arrival process, including QR code scanning and external LDAP authentication logic. - Structured sequential data entry steps for fetching data, entering vitals (Weight, Temp, BP), and creating a Visit ID. - Integrated queue management logic (Add Patient to Doctor Queue) and added a Patient State Manager decision node (Admit, Discharge, OPD). | 1 | Chaitanya | https://drive.google.com/file/d/1TTf3G-PR39vSZLFndX0X5-yxjv814HQ_/view?usp=sharing
2026-02-04 | Activity - Doctor | - Isolated the clinical workflow into a dedicated, dashboard-driven Activity Diagram. - Separated parallel non-clinical tasks (Set Availability, View Schedule) from the core consultation flow. - Structured the detailed consultation lifecycle: Queue appearance -> Select -> Confirm Identity -> Claim -> Retrieve History -> Consult -> Prescribe. - Retained the "Lab Test Required?" conditional logic but integrated it explicitly before saving consultation details. | 1 | Chaitanya | https://drive.google.com/file/d/1TlgiC4ZSoVbakLMwFOad-B_0Koz3dxsy/view?usp=sharing
2026-02-14 | Activity - Pharmacy | - Separated pharmacy operations into a distinct, modular workflow. - Modeled queue-based processing (View Prescription Queue -> Select by Visit ID). - Introduced crucial inventory validation logic via the "All Medicines Available?" decision node. - Added alternative path handling for partial/out-of-stock scenarios (Notify, Update Status) alongside the standard dispensing, billing, and inventory update flow. | 1 | Chaitanya, Yash | https://drive.google.com/file/d/19Ovv2M3huZmrernyMg6lMM3idtHyTM7e/view?usp=sharing
2026-02-14 | Activity - Activity (Final Review & Alignment) | - Reviewed all modular activity diagrams (Patient, Reception, Doctor, Pharmacy) for cross-functional consistency. - Verified that state transitions and handoffs between the isolated flows (e.g., Reception adding to queue -> Doctor retrieving from queue) align correctly. - Conducted minor layout and alignment adjustments to improve visual readability. - Confirmed no structural logic changes were required for this iteration. | 2 | Chaitanya, Nayan, Yash
Class Diagram
2026-01-21 | Class (Initial Conceptual Model) | - Created initial structural model mapping basic domain entities. - Established a simple inheritance hierarchy from a base User class to Admin, Doctor, and Patient. - Modeled direct, simple associations between Patient and core records (Appointment, MedicalRecord, Prescription). - Captured rudimentary attributes and methods (e.g., login(), bookAppointment()) without specific data types. - Included legacy entities like Ambulance reflecting the early project scope. | 0 | Yash, Nayan | https://drive.google.com/file/d/1z_UV8vHs-kXd5dj8_Ws85YjURRN9W2aO/view?usp=sharing
2026-02-04 | Class (Refined Structural Architecture) | - Expanded the User inheritance hierarchy to include all system staff actors: PharmacyStaff, ReceptionStaff, and LabStaff. - Introduced Visit as a central, aggregating entity to link patients, doctors, prescriptions, bills, and lab reports. - Defined explicit enumerations (UserRole, DoctorType, VisitStatus) to enforce domain constraints. - Detailed attributes with specific data types (UUID, DateTime, Blob) and expanded method signatures (e.g., scanQRCode(), updateInventory()). - Introduced system-level utility and service classes (NotificationService, InventoryItem) with explicit dependency tracking (dashed lines). - Removed out-of-scope classes (Ambulance) and refactored redundant classes (e.g., MedicalRecord replaced by Visit history and ExternalDocument). | 1 | Nayan | https://drive.google.com/file/d/1XNxNrzIrAyX6fzJxwxKTzmJkp7dRVIfd/view?usp=sharing
2026-02-04 | Class (Final Review & Alignment) | - Reviewed and validated the V2.0 class model against final system requirements and sequence diagram interactions. - Verified that attribute data types and method signatures align with the planned database schema and implementation logic. - Conducted minor layout and routing adjustments to improve structural readability without changing core logic. - Confirmed class relationships (multiplicities and associations) fully support all modeled use case constraints. | 2 | Yash, Nayan, Chaitanya | '
Sequence Diagram
2026-01-21 | Sequence (Initial Booking Interaction) | - Created initial high-level sequence diagram to capture the basic patient lifecycle. - Modeled a simplified architecture using generic, monolithic lifelines (System, Database) alongside primary actors (Patient, Doctor, Pharmacy). - Mapped a linear, synchronous flow covering basic booking, history retrieval, prescription storage, and billing. - Excluded specific API routes, microservices, or detailed database query logic. | 0 | Nayan, Yash | https://drive.google.com/file/d/1vWoZoZ51Y__kxBKnAUgbbs5fT4jrC28l/view?usp=sharing
2026-02-04 | Sequence (End-to-End System Architecture) | - Transitioned from monolithic system lifelines to a detailed service-oriented architecture (e.g., Auth Controller, Scheduling & Attendance Service, Notification Service). - Segmented the diagram into logical requirement-based interaction frames (e.g., Doctor Availability, Patient Registration, Lab Test Workflow). - Replaced generic messages with explicit REST-like API endpoints (e.g., POST /api/visits/V101/claim). - Upgraded the generic database lifeline to a specific PostgreSQL instance, mapping exact SQL operations (INSERT, UPDATE, SELECT) to system events. - Expanded the actor scope to include Receptionist and Lab Tech, aligning with updated Use Case and Activity models. - Modeled asynchronous background tasks, such as broadcast messages via the Notification Service and overtime calculation upon checkout. | 1 | Nayan, | https://drive.google.com/file/d/1NCujvKQOCciue9CcVtX0pwaQEwZT-8GK/view?usp=sharing
2026-02-14 | Sequence (Final Review & Alignment) | - Reviewed and validated V2.0 interactions against the detailed methods and attributes defined in the V2.0 Class Diagram. - Cross-checked database operations (SQL queries) against the defined entity relationships. - Ensured all API calls correctly mapped to the state transitions outlined in the modular Activity diagrams. - Conducted minor formatting adjustments to lifelines and activation boxes for clarity. | 2 | Yash, Nayan, Chaitanya | *same as above 1.0*
Component Diagram
2026-01-21 | Component | - No component diagram was created for the initial conceptual phase of the SRS document. | 0
2026-02-04 | Component (System Architecture Introduced) | - Created the initial Component Diagram to define the physical and logical architecture of the PHC Integrated Digital System. - Structured the architecture into three primary internal layers: Frontend Presentation Layer, Backend Business Logic, and PostgreSQL Data Store. - Defined specific backend management modules (e.g., Patient & Records Manager, Scheduling & Attendance, Auth Manager, Clinical Services Core). - Mapped logical database collections (e.g., Patients/Docs, Inventory/Bills) directly to their corresponding backend services. - Modeled integrations with External Infrastructure, explicitly showing connections to the IITJ LDAP (for authentication) and an Email Gateway (for the Notification Service). | 1 | Yash, Nayan, Chaitanya | https://drive.google.com/file/d/1b6nz4kjKqxgDviFHFB_WBZ5nnV4T_Fyl/view?usp=sharing
2026-02-14 | Component (Final Review & Alignment) | - Reviewed the newly introduced component architecture to ensure it fully supports the API routes defined in the V2.0 Sequence Diagram. - Verified that all backend components align with the isolated actor workflows established in the V2.0 Activity Diagrams. - Confirmed external system dependencies (LDAP, Email) are correctly represented. | 2 |  | no further changes

## Implementation
Requirements (Functional / Non-functional / Business) | Component | Class | Functions | Start Date of Code | End Date of Code | Update Date | Update Made | URL of Change | Reason for Update | Team Member(s) Designing / Updating Code | Test / Integration Status Details
[11 empty] | Team Member(s) Testing Code | Complete / Ongoing / Abandoned | Ticket_ids raised | Date of Ticket Generation | Date of Ticket Resolution
NFR-01, NFR-02, NFR-03 | QA & Test Infrastructure | - | smoke_test.sh (59 smoke checks), test_cases.csv (48 documented TCs), e2e-full-flow.js, VHS tape recordings | 2026-03-18 | 2026-03-25 | 2026-03-25 | Expanded automated test coverage to 59 smoke checks, retained 48 categorized documented CSV test cases, and added full-system end-to-end flow validation | Commits 8f0f443, f2b7f20, ec4a4cb, 3fac9c2 | Lab 7 & 8 Testing Assignment + Sprint 5 Integration | Nayan, Chaitanya, Yash | Chaitanya, Nayan | Complete | #16 | 2026-03-18 | 2026-03-25
NFR-Security | Auth Manager | AuthService, LDAP Docker Setup | loginUser, LDAP bind validation | 2026-03-25 | 2026-03-25 | 2026-03-25 | Replaced the LDAP fallback-only behavior with local Dockerized LDAP-backed authentication for seeded users | Commit 9e3e7c0 (2026-03-25) | Sprint 5 Security / Integration | Yash, Chaitanya | Yash, Nayan | Complete | #17 | 2026-03-25 | 2026-03-25
NFR-Integration, NFR-Documentation | QA & Integration | E2E Runner, API Documentation | test:e2e, migrate:deploy, route index maintenance | 2026-03-25 | 2026-03-25 | 2026-03-25 | Added full-system end-to-end flow runner and API documentation for backend integration closeout | Commits 3fac9c2, 2d7e421 (2026-03-25) | Sprint 5 Integration | Yash, Chaitanya | Yash, Nayan | Complete | #18 | 2026-03-25 | 2026-03-25
REQ-40, REQ-41 | Notification & Availability | DoctorController, NotificationController | markUnavailable, listMyNotifications, markNotificationRead | 2026-03-25 | 2026-03-25 | 2026-03-25 | Added physician absence workflow and in-app availability notifications for affected users | Commit 9182fcc (2026-03-25) | Sprint 5 Implementation | Yash, Nayan | Chaitanya, Nayan | Complete | #19 | 2026-03-25 | 2026-03-25
REQ-49 | Admin User Management | AdminController | createUser, listUsers, updateUser | 2026-03-24 | 2026-03-24 | 2026-03-24 | Added admin user creation, filtering, role update, deactivation, and account status controls | Commit 5ff16c2 (2026-03-24) | Sprint 5 Implementation | Yash, Chaitanya | Chaitanya, Nayan | Complete | #20 | 2026-03-24 | 2026-03-24
REQ-50, REQ-52 | Reporting & Admin | ReportController | usage, attendanceSummary | 2026-03-24 | 2026-03-24 | 2026-03-24 | Added usage and attendance summary reporting endpoints for admin review | Commit 248d70a (2026-03-24) | Sprint 5 Implementation | Yash, Nayan | Chaitanya, Nayan | Complete | #21 | 2026-03-24 | 2026-03-24
REQ-51 | Public Information & Admin | EventController | publish, listUpcomingEvents | 2026-03-24 | 2026-03-24 | 2026-03-24 | Added PHC event publishing and public upcoming-events listing | Commit b66f7f2 (2026-03-24) | Sprint 5 Implementation | Yash, Chaitanya | Chaitanya, Nayan | Complete | #22 | 2026-03-24 | 2026-03-24
REQ-57 | Patient & Records Manager | PatientController | getMyLabReportsList | 2026-03-24 | 2026-03-24 | 2026-03-24 | Added patient self-service access to their own lab reports with role-safe filtering | Commit 7718df7 (2026-03-24) | Sprint 5 Implementation | Yash, Chaitanya | Chaitanya, Nayan | Complete | #23 | 2026-03-24 | 2026-03-24
REQ-56, REQ-57 | Laboratory Manager | LabController | getLabRequestById | 2026-03-24 | 2026-03-24 | 2026-03-24 | Added single lab-request detail endpoint with role-based access checks | Commit f1ef67b (2026-03-24) | Sprint 5 Implementation | Chaitanya, Nayan | Chaitanya, Nayan | Complete | #24 | 2026-03-24 | 2026-03-24
REQ-16, REQ-17, REQ-21, REQ-22, REQ-24, REQ-28 | Clinical Services Core | VisitController | createVisit, getMyQueue, getVisitRecord, recordVitals, claimVisit, saveClinicalNotes, completeVisit, cancelVisit | 2026-02-09 | 2026-02-15 | 2026-02-18 | Implemented visit lifecycle routes | Commit 8f634a0 |  | Chaitanya, Yash | Chaitanya, Yash | Complete | #7 | 2026-02-09 | 2026-02-15
REQ-10, REQ-15 | Patient & Records Manager | PatientController | getMyProfile, updateProfile, identifyByQR, getPatientRecord, getVisitHistory | 2026-02-03 | 2026-02-06 | 2026-02-07 | Added patient profile and QR identification routes | Commit 7f7b2d7 |  | Yash, Nayan | Yash, Nayan | Complete | #6 | 2026-02-03 | 2026-02-06
NFR-Security | Auth Manager | AuthController | login, getCurrentUser, verifyJWT, authorizeRoles | 2026-02-01 | 2026-02-05 | 2026-02-06 | Implemented JWT auth with LDAP stub | Commit 01492a8 |  | Yash, Nayan | Yash, Nayan | Complete | #5 | 2026-02-01 | 2026-02-05
NFR-Architecture | Backend Core | Middleware, Config | errorHandler, loadConfig | 2026-01-26 | 2026-01-29 | 2026-02-01 | Added constants, config, error handler middleware | Commit b7768e3 | Setup core application architecture | Yash, Nayan | Yash, Nayan | Complete | #4 | 2026-01-26 | 2026-01-29
BR-Schema | PostgreSQL Data Store | PrismaSchema | migrate | 2026-01-27 | 2026-01-31 | 2026-02-03 | Aligned Prisma schema with SRS 2.0 | Commit 40b6d1a | Database schema update to match SRS v2.0 | Yash, Nayan | Yash, Nayan | Complete | #3 | 2026-01-27 | 2026-01-31
REQ-57 | Patient & Records Manager | PatientController | getMyLabReportsList | 46100 | 46105 | 46105 | Added patient self-service access to their own lab reports with role-safe filtering | Commit 7718df7 | Sprint 5 Implementation | Yash, Chaitanya | Chaitanya, Nayan | Complete | #17 | 46100 | 46105
REQ-51 | Public Information & Admin | EventController | publish, listUpcomingEvents | 46100 | 46105 | 46105 |  | Commit b66f7f2 | Sprint 5 Implementation | Yash, Chaitanya | Chaitanya, Nayan | Complete | #18 | 46100 | 46105
REQ-50, REQ-52 | Reporting & Admin | ReportController | usage, attendanceSummary | 46100 | 46105 | 46105 | Added usage and attendance summary reporting endpoints for admin review | Commit 248d70a | Sprint 5 Implementation | Yash, Nayan | Chaitanya, Nayan | Complete | #19 | 46100 | 46105
REQ-56, REQ-57 | Laboratory Manager | LabController | getLabRequestById | 46100 | 46105 | 46105 | Added single lab-request detail endpoint with role-based access checks | Commit f1ef67b | Sprint 5 Implementation | Chaitanya, Nayan | Chaitanya, Nayan | Complete | #20 | 46100 | 46105
REQ-49 | Admin User Management | AdminController | createUser, listUsers, updateUser | 46100 | 46105 | 46105 | Added admin user creation, filtering, role update, deactivation, and account status controls | Commit 5ff16c2 | Sprint 5 Implementation | Yash, Chaitanya | Chaitanya, Nayan | Complete | #21 | 46100 | 46105
REQ-40, REQ-41 | Notification & Availability | DoctorController, NotificationController | markUnavailable, listMyNotifications, markNotificationRead | 46100 | 46106 | 46106 | Added physician absence workflow and in-app availability notifications for affected users | Commit 9182fcc | Sprint 5 Implementation | Yash, Nayan | Chaitanya, Nayan | Complete | #22 | 46100 | 46106
NFR-Integration, NFR-Documentation | QA & Integration | E2E Runner, API Documentation | test:e2e, migrate:deploy, route index maintenance | 46100 | 46106 | 46106 | Added full-system end-to-end flow runner and API documentation for backend integration closeout | Commits 3fac9c2, 2d7e421 | Sprint 5 Integration | Yash, Chaitanya | Yash, Nayan | Complete | #23 | 46100 | 46106
NFR-Security | Auth Manager | AuthService, LDAP Docker Setup | loginUser, LDAP bind validation | 46100 | 46106 | 46106 | Replaced the LDAP fallback-only behavior with local Dockerized LDAP-backed authentication for seeded users | Commit 9e3e7c0 | Sprint 5 Security / Integration | Yash, Chaitanya | Yash, Nayan | Complete | #24 | 46100 | 46106

## Alpha Cards Progress
|  | Alpha Manager | Alpha
|  | Chaitanya Singh | Stakeholders, Opportunity, Work
|  | Bavadiya Yash | Software System, Team
|  | Nayan | Requirements, Way of Working
Alpha (Category) | State Name | Checklist Item Description | Progress (%) | Status | Alpha manager | Remark | Date
Stakeholders | Recognized | Stakeholder groups identified | 100 | TRUE | Chaitanya Singh | PHC staff, doctors, and students defined in SRS 1.0 | 2026-01-24
Stakeholders | Recognized | Key stakeholder groups represented | 100 | TRUE | Chaitanya Singh | Project leads assigned for communication. | 2026-01-24
Stakeholders | Recognized | Responsibilities defined | 100 | TRUE | Chaitanya Singh | SRS outlines user class characteristics. | 2026-01-24
Stakeholders | Represented | Responsibilities agreed | 100 | TRUE | Chaitanya Singh | Approved in SRS v2.0 formal submission. | 2026-02-07
Stakeholders | Represented | Representatives authorized | 100 | TRUE | Chaitanya Singh | Yash, Chaitanya, Nayan designated. | 2026-02-07
Stakeholders | Represented | Collaboration approach agreed | 100 | TRUE | Chaitanya Singh | Bi-weekly sprints and Trello tracking. | 2026-02-07
Stakeholders | Represented | Way of working supported & respected | 100 | TRUE | Chaitanya Singh | Agile methodology documented. | 2026-02-07
Stakeholders | Involved | Representatives assist the team | 100 | TRUE | Chaitanya Singh | Iterative feedback gathered for revisions. | 2026-02-21
Stakeholders | Involved | Timely feedback and decisions provided | 100 | TRUE | Chaitanya Singh | Revisions 1.1–2.0 reflect prompt updates. | 2026-02-21
Stakeholders | Involved | Changes promptly communicated | 100 | TRUE | Chaitanya Singh | Version history tracks major scope changes. | 2026-02-21
Stakeholders | In Agreement | Minimal expectations agreed | 100 | TRUE | Chaitanya Singh | Functional priorities (High/Medium) set. | 2026-02-21
Stakeholders | In Agreement | Reps happy with their involvement | 100 | TRUE | Chaitanya Singh | Continuous feedback loop established. | 2026-02-21
Stakeholders | In Agreement | Reps input valued | 100 | TRUE | Chaitanya Singh | Adjustments made to LDAP and DB design. | 2026-02-21
Stakeholders | In Agreement | Team's input valued | 100 | TRUE | Chaitanya Singh | Team decisions reflected in architecture. | 2026-02-21
Stakeholders | In Agreement | Priorities clear & perspectives balanced | 100 | TRUE | Chaitanya Singh | Core clinical workflows prioritized over ambulance module. | 2026-02-21
Stakeholders | Satisfied for Deployment | Stakeholder feedback provided | 0 | FALSE
Stakeholders | Satisfied for Deployment | System ready for deployment | 0 | FALSE
Stakeholders | Satisfied in Use | Feedback on system use available | 0 | FALSE
Stakeholders | Satisfied in Use | System meets expectations | 0 | FALSE
Opportunity | Identified | Idea behind opportunity identified | 100 | TRUE | Chaitanya Singh | Digitizing manual PHC records. | 2026-01-24
Opportunity | Identified | At least one investing stakeholder interested | 100 | TRUE | Chaitanya Singh | Institutional authorities aligned. | 2026-01-24
Opportunity | Identified | Other stakeholders identified | 100 | TRUE | Chaitanya Singh | Doctors and admin staff mapped. | 2026-01-24
Opportunity | Solution Needed | Solution identified | 100 | TRUE | Chaitanya Singh | Integrated digital portal proposed. | 2026-02-07
Opportunity | Solution Needed | Stakeholders' needs established | 100 | TRUE | Chaitanya Singh | Need for centralized data and automated workflow confirmed. | 2026-02-07
Opportunity | Solution Needed | Problems and root causes identified | 100 | TRUE | Chaitanya Singh | Paperwork delays and data loss noted. | 2026-02-07
Opportunity | Solution Needed | Need for a solution confirmed | 100 | TRUE | Chaitanya Singh | SRS v1.0 baseline accepted | 2026-02-07
Opportunity | Solution Needed | At least one solution proposed | 100 | TRUE | Chaitanya Singh | Web-based system design approved. | 2026-02-07
Opportunity | Value Established | Opportunity value quantified | 100 | 1 | Chaitanya Singh | Lab 9/10 metrics now quantify response times, throughput, burn trends, and code size. | 2026-04-03
Opportunity | Value Established | Solution impact understood | 100 | TRUE | Chaitanya Singh | Clear impact on prescription and lab tracking. | 2026-02-21
Opportunity | Value Established | System value understood | 100 | TRUE | Chaitanya Singh | Improved data integrity and accessibility. | 2026-02-21
Opportunity | Value Established | Success criteria clear | 100 | TRUE | Chaitanya Singh | Documented in non-functional requirements. | 2026-02-21
Opportunity | Value Established | Outcomes clear and quantified: | 100 | TRUE | Chaitanya Singh | Specific workflow metrics targeted. | 2026-02-21
Opportunity | Viable | Solution outlined | 100 | TRUE | Chaitanya Singh | Full UML diagrams (Use Case, Class, Component) complete. | 2026-02-21
Opportunity | Viable | Solution possible within constraints | 100 | TRUE | Chaitanya Singh | Local hosting with PostgreSQL confirmed feasible. | 2026-02-21
Opportunity | Viable | Risks acceptable & manageable | 100 | TRUE | Chaitanya Singh | Security and LDAP failover risks assessed. | 2026-02-21
Opportunity | Viable | Solution profitable | 100 | 1 | Chaitanya Singh | Campus-scale backend completion and reused open-source tooling keep the solution practical for the project scope. | 2026-04-03
Opportunity | Viable | Reasons to develop solution understood | 100 | TRUE | Chaitanya Singh | Clear alignment with institutional needs. | 2026-02-21
Opportunity | Viable | Pursuit viable | 100 | TRUE | Chaitanya Singh | Sprint plan 0-7 confirmed. | 2026-02-21
Opportunity | Addressed | Opportunity addressed | 75 | 0 |  | The backend opportunity is substantially addressed through Sprint 5, but Sprint 6 frontend work is still pending. | 2026-04-03
Opportunity | Addressed | Solution worth deploying | 0
Opportunity | Addressed | Stakeholders satisfied | 0
Opportunity | Benefit Accrued | Solution accrues benefits | 0
Opportunity | Benefit Accrued | ROI acceptable | 0
Software System | Architecture Selected | Architecture selection criteria agreed | 100 | TRUE | Bavadiya Yash | Performance and security requirements met. | 2026-02-07
Software System | Architecture Selected | HW platform identified | 100 | TRUE | Bavadiya Yash | Generic x86_64 server environments targeted. | 2026-02-07
Software System | Architecture Selected | Technologies selected | 100 | TRUE | Bavadiya Yash | PostgreSQL, Linux, Web frontend. | 2026-02-07
Software System | Architecture Selected | System boundary known | 100 | TRUE | Bavadiya Yash | Scope bounded to clinical workflows. | 2026-02-07
Software System | Architecture Selected | Decisions on system organization made | 100 | TRUE | Bavadiya Yash | Layered architecture pattern established. | 2026-02-07
Software System | Architecture Selected | Buy, build, reuse decisions made | 100 | TRUE | Bavadiya Yash | Custom build with open-source stack. | 2026-02-07
Software System | Architecture Selected | Key technical risks agreed to | 100 | 1 | Bavadiya Yash | LDAP, integration, and documentation-drift risks are explicitly captured in the Lab 9/10 risk matrix. | 2026-04-03
Software System | Demonstrable | Key architectural characteristics demonstrated | 100 | 1 |  | The backend architecture is demonstrable through live route modules, Prisma schema, and integrated flows. | 2026-04-03
Software System | Demonstrable | System exercised & performance measured | 100 | 1 |  | Performance has been measured through smoke timings, repeatability checks, and Lab 9/10 analysis. | 2026-04-03
Software System | Demonstrable | Critical HW configurations demonstrated | 0
Software System | Demonstrable | Critical interfaces demonstrated | 100 | 1 |  | Critical interfaces including Prisma/Postgres, JWT auth, LDAP, and Bruno-tested APIs are demonstrated. | 2026-04-03
Software System | Demonstrable | Integration with environment demonstrated | 100 | 1 |  | Local LDAP, database migrations, and end-to-end HTTP flow demonstrate integration with the intended environment. | 2026-04-03
Software System | Demonstrable | Architecture accepted as fit-for-purpose | 75 | 0 |  | Accepted as fit-for-purpose for backend scope; full product acceptance still depends on Sprint 6 and Sprint 7. | 2026-04-03
Software System | Usable | System can be operated | 75 | 0 |  | The backend is operable through API flows, though the final user-facing frontend is not yet built. | 2026-04-03
Software System | Usable | System functionality tested | 100 | 1 |  | Functionality is covered by 48 documented test cases, expanded smoke coverage, and an end-to-end runner. | 2026-04-03
Software System | Usable | System performance acceptable | 100 | 1 |  | Measured response times remain within stated thresholds for login, retrieval, billing, and QR check-in. | 2026-04-03
Software System | Usable | Defect levels acceptable | 0
Software System | Usable | System fully documented | 75 | 0 |  | Backend documentation is strong; final user/deployment documentation still belongs to later sprints. | 2026-04-03
Software System | Usable | Release content known | 100 | 1 |  | Sprint 0-5 backend release content is clear and documented in README, TESTING, and Lab 9/10 artifacts. | 2026-04-03
Software System | Usable | Added value clear | 100 | 1 |  | Added value is clear through reduced paperwork, traceable visit linkage, and role-safe workflow automation. | 2026-04-03
Software System | Ready | User documentation available | 0
Software System | Ready | System accepted as fit-for-purpose | 0
Software System | Ready | Stakeholders want the system | 0
Software System | Ready | Operational support in place | 0
Software System | Operational | System available for use | 0
Software System | Operational | System live | 0
Software System | Operational | Agreed service levels supported | 0
Software System | Retired | Replaced or discontinued | 0
Software System | Retired | No longer supported | 0
Software System | Retired | No authorized users | 0
Software System | Retired | Updates stopped | 0
Requirements | Conceived | Stakeholders agree system is to be produced | 100 | TRUE | Nayan | Approval to proceed with SRS drafting granted. | 2026-01-24
Requirements | Conceived | Users identified | 100 | TRUE | Nayan | Roles mapped in Use Case diagrams. | 2026-01-24
Requirements | Conceived | Funding stakeholders identified | 100 | TRUE | Nayan | Institutional resources allocated. | 2026-01-24
Requirements | Conceived | Opportunity clear | 100 | TRUE | Nayan | Problem statement defined in SRS. | 2026-01-24
Requirements | Bounded | Development stakeholders identified | 100 | TRUE | Nayan | Team members assigned. | 2026-02-07
Requirements | Bounded | System purpose agreed | 100 | TRUE | Nayan | Scope explicitly defined. | 2026-02-07
Requirements | Bounded | System success clear | 100 | TRUE | Nayan | Testable requirements established. | 2026-02-07
Requirements | Bounded | Shared solution understanding exists | 100 | TRUE | Nayan | SRS formalized and signed off. | 2026-02-07
Requirements | Bounded | Requirements format agreed | 100 | TRUE | Nayan | IEEE 830 format applied. | 2026-02-07
Requirements | Bounded | Requirements management in place | 100 | TRUE | Nayan | REQ-XX identifier system active. | 2026-02-07
Requirements | Bounded | Prioritization scheme clear | 100 | TRUE | Nayan | High, Medium, Low flags used. | 2026-02-07
Requirements | Bounded | Constraints identified & considered | 100 | TRUE | Nayan | Network and operational limits documented. | 2026-02-07
Requirements | Bounded | Assumptions clear | 100 | TRUE | Nayan | Section 2.7 of SRS documented. | 2026-02-07
Requirements | Coherent | Requirements shared | 100 | TRUE | Nayan | SRS v2.0 distributed. | 2026-02-21
Requirements | Coherent | Requirements' origin clear | 100 | TRUE | Nayan | Traceability matrix initiated. | 2026-02-21
Requirements | Coherent | Rationale clear | 100 | TRUE | Nayan | Business logic documented. | 2026-02-21
Requirements | Coherent | Conflicts addressed | 100 | TRUE | Nayan | Ambulance module removed to focus scope. | 2026-02-21
Requirements | Coherent | Essential characteristics clear | 100 | TRUE | Nayan | Core features defined. | 2026-02-21
Requirements | Coherent | Key usage scenarios explained | 100 | TRUE | Nayan | Activity and Sequence diagrams created. | 2026-02-21
Requirements | Coherent | Priorities clear | 100 | TRUE | Nayan | Phased sprint implementation. | 2026-02-21
Requirements | Coherent | Impact understood | 100 | TRUE | Nayan | System dependencies mapped. | 2026-02-21
Requirements | Coherent | Team knows & agrees on what to deliver | 100 | TRUE | Nayan | Sprint plans finalized. | 2026-02-21
Requirements | Acceptable | Acceptable solution described | 100 | TRUE | Nayan | SRS formally submitted. | 2026-02-21
Requirements | Acceptable | Change under control | 100 | TRUE | Nayan | Version history and manager tracking active. | 2026-02-21
Requirements | Acceptable | Value to be realized clear | 100 | TRUE | Nayan | Documented in Introduction. | 2026-02-21
Requirements | Acceptable | Clear how opportunity addressed | 100 | TRUE | Nayan | Mapped to specific modules. | 2026-02-21
Requirements | Acceptable | Testable | 100 | TRUE | Nayan | Verification artifacts linked. | 2026-02-21
Requirements | Addressed | Enough addressed to be acceptable | 75 | 0 |  | Enough requirements are addressed for backend acceptance, with frontend dashboards still pending. | 2026-04-03
Requirements | Addressed | Requirements and system match | 90 | 0 |  | The implemented backend matches the major SRS workflows through Sprint 5. | 2026-04-03
Requirements | Addressed | Value realized clear | 75 | 0 |  | Value realization is visible in backend modules and test evidence, though the full user-facing product is incomplete. | 2026-04-03
Requirements | Addressed | System worth making operational | 75 | 0 |  | The system is worth making operational after frontend completion and Sprint 7 hardening. | 2026-04-03
Requirements | Fulfilled | Stakeholders accept requirements | 0
Requirements | Fulfilled | No hindering requirements | 0
Requirements | Fulfilled | Requirements fully satisfied | 0
Work | Initiated | Required result clear | 100 | TRUE | Chaitanya Singh | SRS approved. | 2026-01-24
Work | Initiated | Constraints clear | 100 | TRUE | Chaitanya Singh | Limitations documented. | 2026-01-24
Work | Initiated | Funding stakeholders known | 100 | TRUE | Chaitanya Singh | Institutional backing. | 2026-01-24
Work | Initiated | Initiator identified | 100 | TRUE | Chaitanya Singh | Project sponsors known. | 2026-01-24
Work | Initiated | Accepting stakeholders known | 100 | TRUE | Chaitanya Singh | Grading authority/PHC admin known. | 2026-01-24
Work | Initiated | Source of funding clear | 100 | TRUE | Chaitanya Singh | Academic project constraints. | 2026-01-24
Work | Initiated | Priority clear | 100 | TRUE | Chaitanya Singh | Delivery dates set. | 2026-01-24
Work | Prepared | Commitment made | 100 | TRUE | Chaitanya Singh | Team agreement signed. | 2026-02-07
Work | Prepared | Cost and effort estimated | 100 | TRUE | Chaitanya Singh | 12-week schedule planned. | 2026-02-07
Work | Prepared | Resource availability understood | 100 | TRUE | Chaitanya Singh | Team capacity mapped. | 2026-02-07
Work | Prepared | Risk exposure understood | 100 | 1 | Chaitanya Singh | Risk exposure is now documented through the Lab 9/10 risk matrix and sprint-mitigation mapping. | 2026-04-03
Work | Prepared | Acceptance criteria established | 100 | TRUE | Chaitanya Singh | Requirement verification set. | 2026-02-07
Work | Prepared | Sufficiently broken down to start | 100 | TRUE | Chaitanya Singh | Tasks added to Trello. | 2026-02-07
Work | Prepared | Tasks identified and prioritized | 100 | TRUE | Chaitanya Singh | Sprints 0-7 mapped. | 2026-02-07
Work | Prepared | Credible plan in place | 100 | TRUE | Chaitanya Singh | Phased delivery scheduled. | 2026-02-07
Work | Prepared | Funding in place | 0 | FALSE | Chaitanya Singh | N/A or institutional support.
Work | Prepared | At least one team member ready | 100 | TRUE | Chaitanya Singh | Entire team active. | 2026-02-07
Work | Prepared | Integration points defined | 100 | TRUE | Chaitanya Singh | Backend/Frontend handoffs set. | 2026-02-07
Work | Started | Development started | 100 | TRUE | Chaitanya Singh | Architecture and visit lifecycles coding active. | 2026-03-07
Work | Started | Progress monitored | 100 | TRUE | Chaitanya Singh | Sprint updates sheet updated. | 2026-03-07
Work | Started | Definition of done in place | 100 | TRUE | Chaitanya Singh | Lab demonstration outputs defined. | 2026-03-07
Work | Started | Tasks being progressed | 100 | TRUE | Chaitanya Singh | Sprint 3 ongoing. | 2026-03-07
Work | Under Control | Tasks being completed | 100 | 1 |  | Sprint 0-5 backend tasks have been completed and tracked against the plan. | 2026-04-03
Work | Under Control | Unplanned work under control | 75 | 0 |  | Unplanned work stayed mostly contained to integration, docs sync, and LDAP hardening. | 2026-04-03
Work | Under Control | Risks under control | 75 | 0 |  | Risks are identified and mitigated, but frontend lag and final hardening still remain. | 2026-04-03
Work | Under Control | Estimates revised to reflect performance | 100 | 1 |  | Schedule understanding has been revised to reflect backend-first delivery and deferred frontend scope. | 2026-04-03
Work | Under Control | Progress measured | 100 | 1 |  | Progress is measured through git history, smoke data, E2E validation, and Lab 9/10 metrics. | 2026-04-03
Work | Under Control | Re-work under control | 75 | 0 |  | Some rework occurred when test coverage expanded and authentication moved from stub logic to local LDAP bind. | 2026-04-03
Work | Under Control | Commitments consistently met | 100 | 1 |  | Sprint 0-5 backend commitments were met; remaining work is intentionally Sprint 6/7 scope. | 2026-04-03
Work | Concluded | Only admin tasks left | 0
Work | Concluded | Results achieved | 0
Work | Concluded | Resulting system accepted | 0
Work | Closed | Lessons learned | 0
Work | Closed | Metrics available | 0
Work | Closed | Everything archived | 0
Work | Closed | Budget reconciled & closed | 0
Work | Closed | Team released | 0
Work | Closed | No outstanding, uncompleted tasks | 0
Way of Working | Principles Established | Team actively support principles | 100 | TRUE | Nayan | Coding conventions followed. | 2026-01-24
Way of Working | Principles Established | Stakeholders agree with principles | 100 | TRUE | Nayan | Development methodology approved. | 2026-01-24
Way of Working | Principles Established | Tool needs agreed | 100 | TRUE | Nayan | GitHub, Trello, PostgreSQL selected. | 2026-01-24
Way of Working | Principles Established | Approach recommended | 100 | TRUE | Nayan | Agile tailored for project. | 2026-01-24
Way of Working | Principles Established | Operational context understood | 100 | TRUE | Nayan | Local institutional network target. | 2026-01-24
Way of Working | Principles Established | Practice & tool constraints known | 100 | TRUE | Nayan | Open-source limitations factored. | 2026-01-24
Way of Working | Foundation Established | Key practices & tools selected | 100 | TRUE | Nayan | Core stack defined. | 2026-02-07
Way of Working | Foundation Established | Practices needed to start work agreed | 100 | TRUE | Nayan | Sprint routines set. | 2026-02-07
Way of Working | Foundation Established | Non-negotiable practices & tools identified | 100 | TRUE | Nayan | camelCase/snake_case rules applied. | 2026-02-07
Way of Working | Foundation Established | Gaps between available and needed way of working understood | 100 | TRUE | Nayan | Learning curves for framework factored. | 2026-02-07
Way of Working | Foundation Established | Gaps in capability understood | 100 | TRUE | Nayan | Learning curves and skill gaps for the selected tech stack (PostgreSQL, web framework) and LDAP integration have been identified and factored into the sprint timelines. | 2026-02-07
Way of Working | Foundation Established | Integrated way of working available | 100 | TRUE | Nayan | Git branching and Trello sync active. | 2026-02-07
Way of Working | In Use | Practices & tools in use | 100 | TRUE | Nayan | Active commits and task moves. | 2026-02-21
Way of Working | In Use | Regularly inspected | 100 | TRUE | Nayan | Bi-weekly sprint reviews. | 2026-02-21
Way of Working | In Use | Adapted to context | 100 | TRUE | Nayan | Tailored specifically for academic timelines. | 2026-02-21
Way of Working | In Use | Supported by team | 100 | TRUE | Nayan | Uniform adoption by Yash, Chaitanya, Nayan. | 2026-02-21
Way of Working | In Use | Feedback mechanisms in place | 100 | TRUE | Nayan | Routine team syncs. | 2026-02-21
Way of Working | In Use | Practices & tools support collaboration | 100 | TRUE | Nayan | Shared repositories active. | 2026-02-21
Way of Working | In Place | Used by whole team | 100 | 1 |  | Shared repo, Trello rhythm, testing assets, and report artifacts are accessible across the full team. | 2026-04-03
Way of Working | In Place | Accessible to whole team | 100 | 1 |  | The agreed way of working is available to the whole team through the repo, tracker, and documented process. | 2026-04-03
Way of Working | In Place | Inspected and adapted by whole team | 100 | 1 |  | The team has repeatedly inspected and adapted the process through SRS updates, testing additions, and Sprint 5 integration work. | 2026-04-03
Way of Working | Working Well | Predictable progress being made | 75 | 0 |  | Progress is broadly predictable, though Sprint 5 still showed late convergence. | 2026-04-03
Way of Working | Working Well | Practices naturally applied | 75 | 0 |  | Practices are consistently applied, but frontend work has not yet exercised the full delivery model. | 2026-04-03
Way of Working | Working Well | Tools naturally support way-of-working | 100 | 1 |  | Git, Bruno, Prisma, Dockerized LDAP, and LaTeX/report tooling now support the team's workflow well. | 2026-04-03
Way of Working | Working Well | Continually tuned | 100 | 1 |  | The way of working has been continually tuned through backend integration, testing expansion, and tracker updates. | 2026-04-03
Way of Working | Retired | No longer in use | 0 | FALSE
Way of Working | Retired | Lessons learned shared | 0 | FALSE
Team | Seeded | Mission defined | 100 | TRUE | Bavadiya Yash | Digitize PHC operations. | 2026-01-24
Team | Seeded | Constraints known and defined | 100 | TRUE | Bavadiya Yash | Time limits established. | 2026-01-24
Team | Seeded | Growth mechanisms in place | 100 | TRUE | Bavadiya Yash | Knowledge sharing active. | 2026-01-24
Team | Seeded | Composition defined | 100 | TRUE | Bavadiya Yash | Three developers. | 2026-01-24
Team | Seeded | Responsibilities outlined | 100 | TRUE | Bavadiya Yash | Specific sprint ownership assigned. | 2026-01-24
Team | Seeded | Required commitment level clear | 100 | TRUE | Bavadiya Yash | Academic credit linked. | 2026-01-24
Team | Seeded | Required competencies identified | 100 | TRUE | Bavadiya Yash | Database, Backend, Frontend skills mapped. | 2026-01-24
Team | Seeded | Size determined | 100 | TRUE | Bavadiya Yash | Fixed at 3. | 2026-01-24
Team | Seeded | Governance rules defined | 100 | TRUE | Bavadiya Yash | Decision making outlined. | 2026-01-24
Team | Seeded | Leadership model selected | 100 | TRUE | Bavadiya Yash | Distributed sprint leads. | 2026-01-24
Team | Formed | Enough members recruited | 100 | TRUE | Bavadiya Yash | Team complete. | 2026-02-07
Team | Formed | Roles understood | 100 | TRUE | Bavadiya Yash | Specialized tasks distributed. | 2026-02-07
Team | Formed | How to work understood | 100 | TRUE | Bavadiya Yash | Agile workflow accepted. | 2026-02-07
Team | Formed | Members introduced | 100 | TRUE | Bavadiya Yash | Existing cohort. | 2026-02-07
Team | Formed | Individual responsibilities accepted and aligned to competencies | 100 | TRUE | Bavadiya Yash | Assignments clear. | 2026-02-07
Team | Formed | Members accepting work | 100 | TRUE | Bavadiya Yash | Sprint backlog distributed. | 2026-02-07
Team | Formed | External collaborators identified | 100 | TRUE | Bavadiya Yash | Evaluators/Advisors known. | 2026-02-07
Team | Formed | Communication mechanisms defined | 100 | TRUE | Bavadiya Yash | Chat and Trello active. | 2026-02-07
Team | Formed | Members commit to team | 100 | TRUE | Bavadiya Yash | Work initiated. | 2026-02-07
Team | Collaborating | Works as one unit | 100 | TRUE | Bavadiya Yash | Cross-functional integration ongoing. | 2026-03-07
Team | Collaborating | Communication is open and honest | 100 | TRUE | Bavadiya Yash | Transparent task tracking. | 2026-03-07
Team | Collaborating | Members support each other | 100 | TRUE | Bavadiya Yash | Shared coding tasks visible. | 2026-03-07
Team | Collaborating | Members believe in the team | 100 | TRUE | Bavadiya Yash | Active progression through sprints. | 2026-03-07
Team | Collaborating | Team has its own identity | 100 | TRUE | Bavadiya Yash | Group 1 established. | 2026-03-07
Team | Performing | Consistently meets its commitments | 75 | 0 |  | The team has met backend commitments consistently through Sprint 5, with frontend delivery still pending. | 2026-04-03
Team | Performing | Continuously improves its way of working | 100 | 1 |  | Continuous improvement is visible in SRS revisions, smoke/e2e additions, and risk/metrics reporting. | 2026-04-03
Team | Performing | Works with minimum supervision | 100 | 1 |  | The team is operating with minimal supervision and self-managed sprint/accountability structure. | 2026-04-03
Team | Performing | Handles changes and challenges effectively | 75 | 0 |  | The team handled scope reduction, LDAP hardening, and integration pressure effectively, with Sprint 6 still to prove UI execution. | 2026-04-03
Team | Adjourned | Team is no longer active | 0 | FALSE
Team | Adjourned | Individual members are released | 0
Team | Adjourned | Team responsibilities are fulfilled or handed over | 0

## Testing
Links : | Testing_Videos | Testing_Script |  | Type Codes Explained ->
F : Functional, N : Negative, B : Boundary, P : Performance/NFR, R : Repeatabillity
TC ID | Type | Module | REQ ID | Test Case Name | Preconditions | Test Steps | Expected Result | Actual Result | Status | Response Time (ms) | Team Member(s) Testing Code | Date
TC-F-001 | Functional | Auth | REQ-01 | Login with valid credentials returns JWT | Server running, doctor01 exists in DB and local LDAP is available | POST /api/v1/auth/login with {ldapId: doctor01, password: doctor01pass} | HTTP 200; response contains accessToken and role=DOCTOR | HTTP 200; accessToken and role=DOCTOR returned | PASS | 78 | Chaitanya, Nayan | 2026-02-06
TC-F-002 | Functional | Auth | REQ-01 | Get current user profile | Valid JWT token in Authorization header | GET /api/v1/auth/me with Bearer token | HTTP 200; response contains userId and role matching login | HTTP 200; userId and role=DOCTOR returned correctly | PASS | 803 | Chaitanya, Nayan | 2026-02-06
TC-F-003 | Functional | Patient | REQ-10 | Patient views own profile | PATIENT JWT for patient01 | GET /api/v1/patients/me with patient token | HTTP 200; response matches patient01 profile | HTTP 200; patient01 name, dob, bloodGroup returned | PASS | 268 | Chaitanya, Nayan | 2026-02-07
TC-F-004 | Functional | Patient | REQ-11 | Patient updates own profile | PATIENT JWT for patient01 | PUT /api/v1/patients/me with {phone: 9999999999} | HTTP 200; updated phone persisted in response | HTTP 200; phone field updated and returned | PASS | 286 | Chaitanya, Nayan | 2026-02-07
TC-F-005 | Functional | Patient | REQ-12 | Reception identifies patient by QR code | RECEPTION_STAFF JWT, QR001 assigned to patient01 | GET /api/v1/patients/qr/QR001 with staff token | HTTP 200; response contains patientId matching patient01 | HTTP 200; patient01 profile returned for QR001 | PASS | 258 | Chaitanya, Yash | 2026-02-07
TC-F-006 | Functional | Checkin | REQ-34 | QR check-in creates visit + vitals atomically | RECEPTION_STAFF JWT, QR001 patient exists | POST /api/v1/checkin with {qrCode: QR001, visitType: OPD, vitals: {weight, temp, bp}} | HTTP 201; visitId returned; patient resolved; vitals stored | HTTP 201; visitId created atomically with vitals linked | PASS | 880 | Chaitanya, Yash | 2026-03-18
TC-F-007 | Functional | Doctor | REQ-20 | Doctor checks in (opens attendance record) | DOCTOR JWT, doctor01 not already checked in | POST /api/v1/doctors/me/checkin with doctor token | HTTP 200; attendanceStatus becomes CHECKED_IN | HTTP 200; attendance record opened; isAvailable=true | PASS | 687 | Yash, Nayan | 2026-02-21
TC-F-008 | Functional | Visit | REQ-21 | Doctor views waiting patient queue | DOCTOR JWT, at least one WAITING visit exists | GET /api/v1/visits/my-queue with doctor token | HTTP 200; list of WAITING visits returned | HTTP 200; visits array with WAITING status returned | PASS | 350 | Yash, Nayan | 2026-02-18
TC-F-009 | Functional | Visit | REQ-22 | Doctor claims visit (status → IN_CONSULTATION) | DOCTOR JWT, visitId in WAITING status | PUT /api/v1/visits/:id/claim with doctor token | HTTP 200; visitStatus changes to IN_CONSULTATION | HTTP 200; visitStatus updated to IN_CONSULTATION | PASS | 338 | Chaitanya, Yash | 2026-02-18
TC-F-010 | Functional | Visit | REQ-24 | Doctor saves consultation notes | DOCTOR JWT, visitId in IN_CONSULTATION | PUT /api/v1/visits/:id/consultation with {consultationNotes: ...} | HTTP 200; notes persisted and returned | HTTP 200; consultationNotes stored in visit record | PASS | 339 | Chaitanya, Yash | 2026-02-18
TC-F-011 | Functional | Prescription | REQ-30 | Doctor creates digital prescription | DOCTOR JWT, visitId in IN_CONSULTATION | POST /api/v1/visits/:id/prescription with medicine list | HTTP 201; prescriptionId returned; isDispensed=false | HTTP 201; prescription created with isDispensed=false | PASS | 1114 | Yash, Nayan | 2026-02-27
TC-F-012 | Functional | Lab | REQ-40 | Doctor requests lab test | DOCTOR JWT, visitId in IN_CONSULTATION | POST /api/v1/visits/:id/lab-requests with {testName: CBC} | HTTP 201; labRequestId returned; status=PENDING | HTTP 201; lab request created with status=PENDING | PASS | 528 | Yash, Nayan | 2026-02-28
TC-F-013 | Functional | Visit | REQ-23 | Doctor completes visit (status → COMPLETED) | DOCTOR JWT, visitId in IN_CONSULTATION | PUT /api/v1/visits/:id/complete with doctor token | HTTP 200; visitStatus=COMPLETED | HTTP 200; visitStatus updated to COMPLETED | PASS | 362 | Yash, Nayan | 2026-02-18
TC-F-014 | Functional | Doctor | REQ-20 | Doctor checks out (closes attendance; computes hours) | DOCTOR JWT, doctor01 currently checked in | POST /api/v1/doctors/me/checkout with doctor token | HTTP 200; attendanceStatus CHECKED_OUT; hoursWorked computed | HTTP 200; attendance record closed; hoursWorked calculated | PASS | 603 | Chaitanya, Yash | 2026-02-21
TC-F-015 | Functional | Prescription | REQ-31 | Pharmacy views undispensed prescription queue | PHARMACY_STAFF JWT | GET /api/v1/prescriptions/pending with staff token | HTTP 200; array of undispensed prescriptions returned | HTTP 200; pending prescriptions list returned | PASS | 870 | Chaitanya, Yash | 2026-02-27
TC-F-016 | Functional | Prescription | REQ-31 | Pharmacy dispenses prescription | PHARMACY_STAFF JWT, undispensed prescriptionId | PUT /api/v1/prescriptions/:id/dispense with staff token | HTTP 200; isDispensed=true | HTTP 200; prescription marked as dispensed | PASS | 236 | Chaitanya, Yash | 2026-02-27
TC-F-017 | Functional | Billing | REQ-50 | Pharmacy generates bill with atomic stock deduction | PHARMACY_STAFF JWT, completedVisitId, medicine in stock | POST /api/v1/visits/:id/bill with {items:[{medicineId, quantity:2}]} | HTTP 201; billId returned; stockQuantity decremented atomically | HTTP 201; bill created; stock decremented by 2 in same transaction | PASS | 1291 | Chaitanya, Nayan | 2026-03-18
TC-F-018 | Functional | Billing | REQ-50 | Pharmacy marks bill as paid | PHARMACY_STAFF JWT, unpaid billId | PUT /api/v1/bills/:id/pay with staff token | HTTP 200; billStatus=PAID | HTTP 200; bill status updated to PAID | PASS | 234 | Chaitanya, Nayan | 2026-03-18
TC-F-019 | Functional | Lab | REQ-41 | Lab staff uploads diagnostic report | LAB_STAFF JWT, pendingLabRequestId | POST /api/v1/lab-requests/:id/report with {reportUrl, findings} | HTTP 201; status=COMPLETED; fileUrl stored | HTTP 201; lab report uploaded; status set to COMPLETED | PASS | 952 | Chaitanya, Nayan | 2026-02-28
TC-F-020 | Functional | Appointment | REQ-32 | Patient books appointment with available doctor | PATIENT JWT, doctor with isAvailable=true | POST /api/v1/appointments with {doctorId, appointmentTime, slotDuration} | HTTP 201; appointmentId returned; status=SCHEDULED | HTTP 201; appointment created with status=SCHEDULED | PASS | 696 | Yash, Nayan | 2026-03-18
TC-F-021 | Functional | Appointment | REQ-33 | Patient cancels appointment | PATIENT JWT, own scheduledAppointmentId | PUT /api/v1/appointments/:id/cancel with patient token | HTTP 200; appointmentStatus=CANCELLED | HTTP 200; appointment status updated to CANCELLED | PASS | 244 | Chaitanya, Nayan | 2026-03-18
TC-F-022 | Functional | Medicine | REQ-50 | Admin adds new medicine to inventory | ADMIN JWT | POST /api/v1/medicines with {name, stockQuantity, unitPrice} | HTTP 201; medicineId returned | HTTP 201; medicine created and returned with assigned ID | PASS | 157 | Yash, Nayan | 2026-03-18
TC-F-023 | Functional | Medicine | REQ-50 | Pharmacy updates medicine stock quantity | PHARMACY_STAFF JWT, existing medicineId | PUT /api/v1/medicines/:id/stock with {stockQuantity: 50} | HTTP 200; updated stockQuantity returned | HTTP 200; stockQuantity updated to requested value | PASS | 240 | Yash, Nayan | 2026-03-18
TC-F-024 | Functional | Document | REQ-35 | Doctor uploads external document for patient | DOCTOR JWT, valid patientId | POST /api/v1/patients/:id/documents with {documentType, fileUrl} | HTTP 201; documentId returned; linked to patient | HTTP 201; document created and linked to patient record | PASS | 315 | Yash, Nayan | 2026-03-18
TC-F-025 | Functional | Document | REQ-35 | View all external documents for patient | DOCTOR JWT, valid patientId | GET /api/v1/patients/:id/documents with doctor token | HTTP 200; array of patient documents returned | HTTP 200; documents array returned for patient | PASS | 730 | Chaitanya, Nayan | 2026-03-18
TC-N-001 | Negative | Auth | REQ-01 | Login with invalid ldapId returns 401 | Server running | POST /api/v1/auth/login with {ldapId: nonexistent, password: x} | HTTP 401; error message returned | HTTP 401; error returned — user not found | PASS | 78 | Yash, Nayan | 2026-02-06
TC-N-002 | Negative | Auth | REQ-01 | Request without token returns 401 | No Authorization header | GET /api/v1/auth/me without token | HTTP 401 Unauthorized | HTTP 401; missing token error returned | PASS | 1 | Yash, Nayan | 2026-02-06
TC-N-003 | Negative | Auth | REQ-01 | Patient accessing pharmacy-only route returns 403 | PATIENT JWT | GET /api/v1/prescriptions/pending with patient token | HTTP 403 Forbidden; RBAC blocks patient | HTTP 403; role not authorized error returned | PASS | 79 | Chaitanya, Yash | 2026-02-06
TC-N-004 | Negative | Billing | REQ-50 | Patient attempting to generate bill returns 403 | PATIENT JWT, valid visitId | POST /api/v1/visits/:id/bill with patient token | HTTP 403 Forbidden | HTTP 403; patient role not permitted to generate bills | PASS | 155 | Chaitanya, Yash | 2026-03-18
TC-N-005 | Negative | Prescription | REQ-30 | Prescription with empty items array returns 400 | DOCTOR JWT, valid visitId | POST /api/v1/visits/:id/prescription with {items:[]} | HTTP 400; items must not be empty | HTTP 400; validation error — items array is empty | PASS | 385 | Chaitanya, Yash | 2026-02-27
TC-N-006 | Negative | Billing | REQ-50 | Bill generation fails when stock insufficient | PHARMACY_STAFF JWT, medicine with stockQuantity=0 | POST /api/v1/visits/:id/bill with quantity > available stock | HTTP 400; insufficient stock; no partial DB update | HTTP 400; stock insufficient error; transaction rolled back | PASS | 390 | Yash, Nayan | 2026-03-18
TC-N-007 | Negative | Visit | REQ-22 | Claiming a COMPLETED visit returns 400 | DOCTOR JWT, visit already COMPLETED | PUT /api/v1/visits/:id/claim on COMPLETED visit | HTTP 400; cannot claim non-WAITING visit | HTTP 400; visit not in WAITING status error | PASS | 163 | Yash, Nayan | 2026-02-18
TC-N-008 | Negative | Prescription | REQ-30 | Duplicate prescription for same visit returns 409 | DOCTOR JWT, visit already has a prescription | POST /api/v1/visits/:id/prescription again | HTTP 409 Conflict | HTTP 409; prescription already exists for this visit | PASS | 389 | Chaitanya, Yash | 2026-02-27
TC-N-009 | Negative | Appointment | REQ-32 | Booking unavailable doctor without emergency flag returns 400 | PATIENT JWT, doctor with isAvailable=false | POST /api/v1/appointments with isEmergency=false | HTTP 400; doctor not available error | HTTP 400; doctor unavailable — set isEmergency:true to override | PASS | 157 | Chaitanya, Yash | 2026-03-18
TC-N-010 | Negative | Checkin | REQ-34 | QR check-in with invalid QR code returns 404 | RECEPTION_STAFF JWT | POST /api/v1/checkin with {qrCode: invalid_code} | HTTP 404; patient not found | HTTP 404; no patient found for provided QR code | PASS | 158 | Chaitanya, Nayan | 2026-03-18
TC-B-001 | Boundary | Prescription | REQ-30 | Prescription with exactly 1 item (minimum valid) returns 201 | DOCTOR JWT, fresh visitId in IN_CONSULTATION | POST /api/v1/visits/:id/prescription with items array of length 1 | HTTP 201; prescription created | HTTP 201; single-item prescription created successfully | PASS | 1031 | Chaitanya, Nayan | 2026-02-27
TC-B-002 | Boundary | Billing | REQ-50 | Bill with quantity = stock exactly (at boundary) returns 201 | PHARMACY_STAFF JWT, medicine with known stock | POST /api/v1/visits/:id/bill with quantity equal to current stock | HTTP 201; bill created; stock drops to 0 | HTTP 201; exact-quantity bill accepted; stockQuantity now 0 | PASS | 1006 | Yash, Nayan | 2026-03-18
TC-B-003 | Boundary | Billing | REQ-50 | Bill with quantity = stock + 1 (over boundary) returns 400 | PHARMACY_STAFF JWT, medicine with known stock | POST /api/v1/visits/:id/bill with quantity one above available stock | HTTP 400; insufficient stock | HTTP 400; over-boundary quantity rejected; stock unchanged | PASS | 409 | Yash, Nayan | 2026-03-18
TC-B-004 | Boundary | Appointment | REQ-32 | Emergency appointment bypasses doctor unavailability | PATIENT JWT, doctor with isAvailable=false | POST /api/v1/appointments with {isEmergency:true, doctorId of unavailable doctor} | HTTP 201; appointment created despite doctor unavailable | HTTP 201; isEmergency=true overrides availability check | PASS | 1250 | Chaitanya, Nayan | 2026-03-18
TC-B-005 | Boundary | Medicine | REQ-50 | Update medicine stock to exactly 0 (valid lower boundary) | PHARMACY_STAFF JWT, existing medicineId | PUT /api/v1/medicines/:id/stock with {stockQuantity: 0} | HTTP 200; stockQuantity set to 0 | HTTP 200; stock set to 0; accepted as valid boundary value | PASS | 232 | Yash, Nayan | 2026-03-18
TC-P-001 | Performance/NFR | Auth | NFR-01 | Login response time under 3000ms | Server under normal load | POST /api/v1/auth/login; measure total response time | HTTP 200 in < 3000ms | HTTP 200 in 77ms — well within 3000ms threshold | PASS | 77 | Yash, Nayan | 2026-03-18
TC-P-002 | Performance/NFR | Patient | NFR-01 | Patient record retrieval under 3000ms | PATIENT JWT, patient profile exists | GET /api/v1/patients/me; measure total response time | HTTP 200 in < 3000ms | HTTP 200 in 233ms — well within 3000ms threshold | PASS | 233 | Yash, Nayan | 2026-03-18
TC-P-003 | Performance/NFR | Prescription | NFR-01 | Prescription retrieval under 3000ms | PHARMACY_STAFF JWT, prescription exists | GET /api/v1/visits/:id/prescription; measure total response time | HTTP 200 in < 3000ms | HTTP 200 in 1215ms — within 3000ms threshold | PASS | 1215 | Yash, Nayan | 2026-03-18
TC-P-004 | Performance/NFR | Billing | NFR-01 | Atomic bill generation under 5000ms | PHARMACY_STAFF JWT, medicine in stock | POST /api/v1/visits/:id/bill; measure total response time | HTTP 201 in < 5000ms (atomic transaction allowed extra) | HTTP 201 in 796ms — within 3000ms threshold | PASS | 1151 | Chaitanya, Nayan | 2026-03-18
TC-P-005 | Performance/NFR | Check in | NFR-01 | Atomic QR check-in under 3000ms | RECEPTION_STAFF JWT, valid QR code | POST /api/v1/checkin with vitals; measure total response time | HTTP 201 in < 3000ms |  | PASS | 796 | Yash, Nayan | 2026-03-18
TC-R-001 | Repeatability | Auth | NFR-01 | Login endpoint consistent under 3000ms (15 runs) | Server running, patient01 seeded | Run POST /api/v1/auth/login 15 consecutive times; record HTTP status and response time per run | All 15 runs HTTP 200 in < 3000ms; no failures | All 15 runs passed — HTTP 200; min=80ms avg=81ms max=85ms | PASS | 81 (avg) | Yash, Nayan | 2026-03-18
TC-R-002 | Repeatability | Patient | NFR-01 | Patient profile retrieval consistent under 3000ms (15 runs) | PATIENT JWT, patient01 profile exists | Run GET /api/v1/patients/me 15 consecutive times; record HTTP status and response time per run | All 15 runs HTTP 200 in < 3000ms; no failures | All 15 runs passed — HTTP 200; min=237ms avg=271ms max=599ms | PASS | 271 (avg) | Chaitanya, Nayan | 2026-03-18
TC-R-003 | Repeatability | Check in | NFR-01 | Atomic QR check-in consistent under 3000ms (15 runs) | RECEPTION_STAFF JWT, QR001 patient exists | Run POST /api/v1/checkin 15 consecutive times; record HTTP status and response time per run | All 15 runs HTTP 201 in < 3000ms; no failures | All 15 runs passed — HTTP 201; min=716ms avg=889ms max=1246ms | PASS | 889 (avg) | Yash, Nayan | 2026-03-18

## Sprint Plans
Sprint | Start Date | End Date | Weeks | Primary Focus | Key Modules | Deliverables / Evidence | SRS Version Alignment | Responsible Leads | Lab Demonstration Output
Sprint 0 | 2026-01-15 | 2026-01-24 | Week 1–2 | Project Initiation & SRS Drafting | Initial requirements + system scope | SRS v1.0 + v1.1 draft | SRS 1.0–1.1 | Yash/Nayan/Chaitanya | Problem definition + initial UML
Sprint 1 | 2026-01-25 | 2026-02-07 | Week 3–4 | Architecture Foundation | LDAP auth + DB schema + patient profile | SRS v1.2–1.6 finalized + schema design | SRS 1.2–1.6 | Yash (arch) Nayan (req) | DB ER + auth flow demo
Sprint 2 | 2026-02-08 | 2026-02-21 | Week 5–6 | Core Clinical Workflow | Visit lifecycle + doctor consultation | SRS v2.0 finalized workflows | SRS 2.0 | Yash/Chaitanya | Visit creation + consultation flow demo
Sprint 3 | 2026-02-22 | 2026-03-07 | Week 7–8 | Diagnostics & Prescription | Prescription + lab modules | Working prescription/lab data model | SRS 2.0 modules | Nayan/Chaitanya | Prescription + lab request demo
Sprint 4 | 2026-03-08 | 2026-03-18 | Week 9–10 | Operational Modules | Pharmacy + billing + QR check-in | Integrated visit→billing flow | SRS 2.0 ops modules | Yash/Nayan | End-to-end PHC workflow demo
Sprint 5 | 2026-03-19 | 2026-04-01 | Week 11–12 | System Integration | Admin + reports + notifications + LDAP + full backend integration | Integrated backend build + E2E flow + API docs + LDAP-backed auth | SRS 2.1-2.2 + testing-aligned backend closeout | Yash (integration), Chaitanya (testing/docs) | API + module integration demo with end-to-end flow
Sprint 6 | 2026-04-02 | 2026-04-15 | Week 13–14 | Frontend & UX Integration | Dashboards + role UI | Role-based UI screens | UI aligned to SRS actors | Chaitanya (UI) | Role dashboards demo
Sprint 7 | 2026-04-16 | 2026-04-20 | Week 15 | Testing & Stabilization | Testing + security + deployment prep | Test report + deployment plan | SRS final compliance | All | Final system demo

## Sprint Updates (hidden)
Sprint | Week Range | Planned Goal | Actual Work Completed | Artifacts Produced | Issues / Blockers | Design Changes / Decisions | Next Sprint Focus | Progress % | Updated By | Date Updated
Sprint 0 | Week 1–2 | SRS draft and backlog creation | Completed problem framing, initial SRS revisions, and the first UML baseline covering core PHC workflows and actors. | SRS 1.0, SRS 1.1, initial use-case/class/activity/component diagrams | Initial scope was too broad because ambulance-related ideas were still included. | Decided to narrow the project to a PHC-centered digital workflow system instead of a larger hospital-style platform. | Finalize architectural foundations, auth design, and database schema. | 100 | Yash / Nayan / Chaitanya | 2026-01-24
Sprint 1 | Week 3–4 | Architecture foundation | Finalized the architecture baseline, schema direction, patient profile routes, JWT auth flow, and the SRS up to v2.0. | SRS 1.2-2.0, Prisma schema, auth middleware, patient profile endpoints, QR identification route | Database provisioning and full LDAP integration were not ready at the same time as the SRS freeze. | Adopted a layered route-controller-service-Prisma backend and kept LDAP fallback in dev until local bind infra was ready. | Implement the core visit lifecycle and doctor workflow. | 100 | Yash / Nayan / Chaitanya | 2026-02-07
Sprint 2 | Week 5–6 | Visit lifecycle implementation | Implemented visit creation, vitals capture, queueing, claim/consult/complete transitions, and doctor availability/check-in/checkout flows. | Visit module, doctor/attendance module, route-level RBAC, Sprint 2 backend commits | Workflow correctness depended heavily on getting visit state transitions right before downstream modules. | Chose visit-centric linkage as the stable backbone for prescriptions, labs, and billing. | Extend the consultation flow into prescriptions and laboratory processing. | 100 | Yash / Chaitanya | 2026-02-21
Sprint 3 | Week 7–8 | Prescription and lab modules | Delivered prescription creation/dispensing and lab request/report flows, then aligned SRS 2.1 and 2.2 with clearer NFR and testing sections. | Prescription module, lab module, SRS 2.1, SRS 2.2, Bruno collection growth | Role-based access for patient-visible lab data needed extra care after the core endpoints were implemented. | Used modular endpoint groups and Bruno-based verification before extending into operational modules. | Integrate operational modules: inventory, billing, appointments, QR check-in, and documents. | 100 | Chaitanya / Nayan / Yash | 2026-03-07
Sprint 4 | Week 9–10 | Pharmacy and billing workflow | Completed medicine inventory, billing with atomic stock deduction, appointments, QR check-in, external document handling, and formal smoke-test artifacts. | Billing module, medicine inventory, appointments, check-in, documents, smoke_test.sh, test_cases.csv, VHS recordings | Documentation synchronization became harder once testing artifacts and operational modules started landing together. | Used Prisma transactions for billing and check-in to keep multi-step operations consistent. | Finish admin and integration scope: user management, events, reports, notifications, real LDAP, and E2E validation. | 100 | Yash / Nayan / Chaitanya | 2026-03-18
Sprint 5 | Week 11–12 | Backend integration | Completed Sprint 5 backend closeout: admin user management, PHC events, usage/attendance reports, patient lab access, notifications, E2E runner, API docs, and local LDAP-backed authentication. | Admin module, report endpoints, notifications, e2e-full-flow.js, API documentation, docker-compose LDAP setup | Most backend closeout work converged in a dense late-sprint batch, increasing pressure on docs and integration visibility. | Replaced the earlier LDAP stub behavior with a real local bind flow and added explicit end-to-end integration verification. | Begin Sprint 6 frontend dashboards while freezing backend scope except for blockers. | 100 | Yash / Chaitanya / Nayan | 2026-04-03
Sprint 6 | Week 13–14 | Frontend dashboards | No production frontend code merged yet. Sprint 6 scope is defined but implementation is intentionally pending while submissions and tracker updates are being completed. | Dashboard scope in README, Lab 9/10 report, role-wise frontend plan | Frontend work has not started in the repository; backend is ahead of UI delivery. | Hold backend scope steady and reuse the stable API surface for role dashboards rather than opening new backend features. | Patient, doctor, reception, pharmacy, lab, and admin dashboard implementation. | 0 | Chaitanya | 2026-04-03
Sprint 7 | Week 15–16 | Testing and stabilization | Not started yet. | Planned: security hardening, load/performance checks, RBAC testing, deployment plan | Pending completion of Sprint 6 UI work. | Sprint 7 remains a stabilization sprint, not a feature-expansion sprint. | Final testing, hardening, and deployment readiness. | 0 | All | 2026-04-03